## Summary
ECET291 - Project Management
First Monday | 2024-09-02
Group |  | Budget | Milestones | Requirements | Team Members |  |  |  | Week 10 | 2024-10-15 | 2024-10-10
Template |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
SmartRecycleBot |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Budget & Milestones? | Updated. Corrections required. | follow up email
RLC |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | PCB working this week? |  | follow up email
AltSpark |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Looks good.
PinballRevival |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Ahead of schedule?
Nautilus |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Updates?
Brübois |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Final Testing starting soon? |  | EC in the works
FLoRa |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Petal v0.1 next week? |  | Plan to update actual expenses in sheet
LapLogic |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Prototype app almost complete?
Fishworks |  | GOOD | GOOD | 13 / 13 | Eric | Kayleb | Sebastien | Braden | 👍
LoopDeck |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Status? |  | Plan to update by Tuesday

## FishWorks
Project FishWorks
Status
Eric | [7 empty] | Planned | Actual | Delta
Kayleb |  |  |  | Budget | GOOD |  |  | 125157.89 | 125213.05 | -55.16
Sebastien |  |  |  | Milestones | GOOD
Braden |  |  |  | Requirements | 13 / 13
Budget
| week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Final
| Monday | 2024-09-02 | 2024-09-09 | 2024-09-16 | 2024-09-23 | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-09
Planned Expenses
Labour |  | 8640 | 8640 | 8640 | 8640 | 8640 | 8640 | 8640 | 8640 | 8640 | 8640 | 8640 | 8640 | 8640 | 8640 | 8640 | 129600
Rent/Facilities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Facilities/Equipment |  | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 12519.9
Supplies |  | 707.27 | 0 | 0 | 0 | 0 | 0 | 0 | 347.76 | 375.64 | 0 | 0 | 556.64 | 0 | 0 | 0 | 1987.31
Weekly |  | 10181.93 | 9474.66 | 9474.66 | 9474.66 | 9474.66 | 9474.66 | 9474.66 | 9822.42 | 9850.3 | 9474.66 | 9474.66 | 10031.3 | 9474.66 | 9474.66 | 9474.66
Cumulative |  | 10181.93 | 19656.59 | 29131.25 | 38605.91 | 48080.57 | 57555.23 | 67029.89 | 76852.31 | 86702.61 | 96177.27 | 105651.93 | 115683.23 | 125157.89 | 134632.55 | 144107.21 | 144107.21
Actual Expenses
Labour |  | 8640 | 8640 | 8640 | 8690 | 8665 | 8640 | 8640 | 8640 | 8640 | 8640 | 8640 | 8640 | 8640 | 8640 | 8640 | 129675
Rent/Facilities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Facilities/Equipment |  | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 834.66 | 12519.9
Supplies |  | 707.27 | 0 | 0 | 302.89 | 143.58 | 167.89 | 397.98 | 22.39 | 0 | 75.47 | 0 | 150 | 0 | 0 | 0 | 1967.47
Weekly |  | 10181.93 | 9474.66 | 9474.66 | 9827.55 | 9643.24 | 9642.55 | 9872.64 | 9497.05 | 9474.66 | 9550.13 | 9474.66 | 9624.66 | 9474.66 | 9474.66 | 9474.66
Cumulative |  | 10181.93 | 19656.59 | 29131.25 | 38958.8 | 48602.04 | 58244.59 | 68117.23 | 77614.28 | 87088.94 | 96639.07 | 106113.73 | 115738.39 | 125213.05 | 134687.71 | 144162.37 | 144162.37
Cumulative Delta |  | 0 | 0 | 0 | 352.89 | 521.47 | 689.36 | 1087.34 | 761.97 | 386.33 | 461.8 | 461.8 | 55.16 | 55.16 | 55.16 | 55.16 | 55.16
Milestones
|  |  |  | Planned | Planned | Actual | Status
Title |  |  |  | Monday | week | week
Tank Basic Set up |  |  | 2024-09-16 |  | 3 | 3 | GOOD
Node Controllers Built |  |  | 2024-10-21 |  | 8 | 7 | GOOD
Base Stations Built |  |  | 2024-10-28 |  | 9 | 7 | GOOD
Hardware Dev Complete |  |  | 2024-11-18 |  | 12 | 11 | GOOD
App Programing Complete |  |  | 2024-11-18 |  | 12 | 11 | GOOD
English Presentation / Functional Demo |  |  | 2024-12-02 |  | 14 | 14
Capstone Symposium |  |  | 2024-12-09 |  | 15 | 15
Requirements
Title |  |  | Owner | Met | Date | Comment
Devices communicate with base station. |  |  | Sebastien | TRUE | 2024-10-08
Base station communicates with MQTT server. |  |  | Sebastien | TRUE | 2024-10-08
Web app connects to MQTT server. |  |  | Sebastien | TRUE | 2024-10-01
Device - Humidity Sensor |  |  | Kayleb | TRUE | 2024-10-18
Device - Air Temperature Sensor |  |  | Kayleb | TRUE | 2024-10-18
Device - Water Temperature Sensor |  |  | Kayleb | TRUE | 2024-10-18
Device - AC Outlet Control |  |  | Eric | TRUE | 2024-11-15
Device - Leak Detection |  |  | Kayleb | TRUE | 2024-10-28
Device – PH Sensor |  |  | Kayleb | TRUE | 2024-11-15
Device - LED Lighting Control |  |  | Kayleb | TRUE | 2024-10-17
Web app UI has widgets for all connected devices |  |  | Kayleb | TRUE | 2024-10-07
Historical data logged on base station SD card |  |  | Sebastien | TRUE | 2024-09-22
Base station can send email warnings and alerts to users |  |  | Sebastien | TRUE | 2024-09-22
Formulas:
Status = IF(D39<TODAY()-5,IF(OR([Planned]<[Actual],[Actual]=0),"MISSED","GOOD"),"")
Status = IF([Planned]<TODAY()-5,IF(OR([Planned]<[Actual],[Actual]=0),"MISSED","GOOD"),"")
Note on F23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Extra 50$ expense on Excel Contractor Reply: That was Braden btw....

## FishWorks_FinalSummary
Final Summary
Group Name: | Project FishWorks
Requirements
Initial Requirement | Modified Requirement | Pass/Fail | EC
Devices communicate with base station. | / | Pass | /
Base station communicates with MQTT server. | / | Pass | /
Web app connects to MQTT server. | / | Pass | /
Device - Humidity Sensor | / | Pass | /
Device - Air Temperature Sensor | / | Pass | /
Device - Water Temperature Sensor | / | Pass | /
Device - AC Outlet Control | / | Pass | /
Device - Leak Detection | / | Pass | /
Device – PH Sensor | Required changing to another brand of pH Sensor | Pass | 001/ Signed
Device - LED Lighting Control | / | Pass | /
Web app UI has widgets for all connected devices | / | Pass | /
Historical data logged on base station SD card | / | Pass | /
Base station can send email warnings and alerts to users | / | Pass | /
Budget
| Amount | EC
Initial Revenue | 144999.72
Initial Expenses | 144462.59
Updated Revenue |  | N/A
Updated Expenses |  | N/A
Actual Revenue | 144999.72
Actual Expenses | 145091.71
Milestones
Initial Milestone | Modified Milestone | Initial Planned Week | Updated Planned Week | Week Met | EC
Tank Basic Set up | / | 3 | / | 3 | /
Node Controllers Built | / | 8 | / | 7 | /
Base Stations Built | / | 9 | / | 7 | /
Hardware Dev Complete | / | 12 | / | 11 | /
App Programing Complete | / | 12 | / | 11 | /
English Presentation / Functional Demo | / | 14 | / |  | /
Capstone Symposium | / | 15 | / |  | /