## 1. Risk Register Template
Project FishWorks: Braden, Sebastien, Eric and Kayleb
This risk assessment is connected to/aligns with: |  | Project FishWorks: FishSense Monitoring and Control Solution
Objective: |  | Is to ensure the safe operation of FishSense and all peripheral devices and mechanical systems.
Date of the risk assessment: |  |  | --------
Risk should be reassessed periodically throughout the life of the program or project.
Future date(s) to reassess the risks within the register: |  |  | --------
NOTE: This template was taken from the BC Governments Risk Management for Government and Provincial Public Sector (Link on following sheet).
RISK MANAGEMENT PROCESS |  | CONTEXT | RISK IDENTIFICATION |  |  |  | ANALYSIS Residual risk rating with treatments in place (For Guidance, See Tab 3) |  |  |  | EVALUATION (For Guidance, See Tab 4) |  |  | TREATMENT MANAGEMENT | [5 empty] | TRACKING |  |  |  | RESIDUAL RISK RATING (Risk rating expected / predicted once all treatments, including additional treatments, are in place.) |  |  |  | CURRENT RISK RATING (Current level of risk in light of treatments implemented at this report period.) |  |  |  | RISK TOLERANCE RATING (Risk tolerance executive is willing to accept. This should be provided by executive after having been briefed on the risk, existing and planned treatments, and associated costs.)
RISK # | CATEGORY | BUSINESS OBJECTIVE/ PRIORITY | RISK EVENT | RISK CAUSE | IMPACT | CURRENT TREATMENTS | L (1-5) | C (1-5) | RISK RATING | HEAT MAP | ADEQUACY OF CURRENT TREATMENTS | ACTION | TREND | ADDITIONAL PLANNED TREATMENT | DELIVERABLES | TASK OWNER | DUE DATE | DEPENDENCIES/ INTER-RELATIONSHIPS | STATUS | PROGRESS % | COMMENTS/ ISSUES | FURTHER ACTION | COMPLETION DATE | L (1-5) | C (1-5) | RISK RATING | HEAT MAP | L (1-5) | C (1-5) | RISK RATING | HEAT MAP | L (1-5) | C (1-5) | RISK RATING | HEAT MAP
Add identifiers to better organize and track risks. | Which category does this Risk Event fall under? | What business objective/priority does this Risk Event affect (e.g., Mandate letter, strategic directive, etc.)? | What events could impact the achievement of objectives (can be positive or negative)? | What Risk Cause (trigger, circumstance, uncertainty) could increase the Likelihood of the Risk Event occurring? There are usually multiple Risk Causes leading to a Risk Event. | How would the Risk Event impact the achievement of the objective/priority? | What Treatments are currently in place to manage the Risk Event? Focus on Treatments that either reduce the Likelihood (column H) of the Risk Event or can reduce the Consequence (column I) if the Risk Event occurs. | How likely? | How severe? | (LxC) | Rating with current treatments in place | Non-existent Inadequate Adequate Robust | Will you do more to manage the risk (treat) or choose to accept and monitor? | If applicable, has this risk rating changed over time? Has column J increased (upward trend), decreased (downward trend) or not changed (static) | What Treatments are needed to further manage the Risk Event? Focus on Treatments that either reduce the Likelihood (column H) of the Risk Event or can reduce the Consequence (column I) if the Risk Event occurs. | Future Treatments will come in what form (e.g., a project plan, a briefing note, report, funding request, other)? | Who will take the lead on this mitigation? | When should the deliverable be ready? (Optional) | Do the Risk Event or Treatments depend on another team or organization? Do they impact another group? | On Track Slowed Stalled |  |  |  |  | How likely? | How severe? | (LxC) | Rating with current treatments in place | How likely? | How severe? | (LxC) | Rating with current treatments in place | How likely? | How severe? | (LxC) | Rating with current treatments in place
1 | Tank/ Mechanical | Presentation/Demo | Tank Leaking | Tank Breaking/ cracking | It would disrupt the pump portion of the presentation, and potential cause health/safety risk due to water/slipping. | We have the tanks on a heavy duty cart that offers several inches of protection in the form of extra shelf space. We take care in where we store it, and are careful of what we allow around or on its cart. | 1 | 4 | 4 | LOW | [13 empty] | 0 | 0 | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
2 | Tank/ Mechanical | Presentation/Demo | Tank Overflowing | Pump siphon fails | It would disrupt the pump portion of the presentation, and potential cause health/safety risk due to water/slipping. | We utilize a 5 minute system where any change to any system that controls the water lever - you must monitor the tank actively for five minutes to ensure that the siphon works as intended. | 1 | 3 | 3 | LOW | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
3 | Tank/ Mechanical | Presentation/Demo | Tank Overflowing | Pump pumps not to the tank | It would disrupt the pump portion of the presentation, and potential cause health/safety risk due to water/slipping. | We utilize a 5 minute system where any change to any system that controls the water lever - you must monitor the tank actively for five minutes to ensure that the siphon works as intended. | 1 | 3 | 3 | LOW | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
4 | Tank/ Mechanical | Presentation/Demo | Electrification | Rogue short allows power to enter the system | It could cause potential health/safety risk due to electricution. | Eric, our resident Red Seal Electrition, has final say on all Line Voltage matters - male GFCI plug end. | 1 | 5 | 5 | LOW | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
5 | Lighting | Presentation/Demo | LEDs overheating | LED Control fails and they get stuck to full power | It would disrupt the lighting portion of the presentation, and potentially cause a fire hazard. | When ever the LED lighting system is on, either manual tempurature checks, or the FishSense monitoring system must be active. | 1 | 3 | 3 | LOW | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
6 | AC-Control | Presentation/Demo | Electrification | AC Control shorts and allows line voltage to enter the system | It would disrupt the pump portion of the presentation, and potential cause health/safety risk due to water/slipping. | Eric, our resident Red Seal Electrition, has final say on all Line Voltage matters - male GFCI plug end. | 1 | 5 | 5 | LOW | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
7 | AC-Control | Presentation/Demo | Pump Runaway | AC Control fails to stop the pump | It would disrupt the pump portion of the presentation, and potential cause health/safety risk due to water/slipping. | We utilize a 5 minute system where any change to any system that controls the water lever - you must monitor the tank actively for five minutes to ensure that the siphon works as intended. | 1 | 3 | 3 | LOW | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
8 | AC-Control | Presentation/Demo | Loss of Basestation Connection | Without the basestation will not beable to control the AC-Control | It would disrupt the pump portion of the presentation, and potential cause health/safety risk due to water/slipping. | We utilize a 5 minute system where any change to any system that controls the water lever - you must monitor the tank actively for five minutes to ensure that the siphon works as intended. | 1 | 3 | 3 | LOW | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
9 | Leak/Level Detect | Presentation/Demo | Tank Overflowing | Device fails to detect level properly | It would disrupt the pump portion of the presentation, and potential cause health/safety risk due to water/slipping. | We utilize a 5 minute system where any change to any system that controls the water lever - you must monitor the tank actively for five minutes to ensure that the siphon works as intended. | 1 | 3 | 3 | LOW | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
10 | Leak/Level Detect | Presentation/Demo | Tank Leaking | Device fails to detect leaks or mis-reads | It would disrupt the pump portion of the presentation, and potential cause health/safety risk due to water/slipping. | We utilize a 5 minute system where any change to any system that controls the water lever - you must monitor the tank actively for five minutes to ensure that the siphon works as intended. We have the tanks on a heavy duty cart that offers several inches of protection in the form of extra shelf space. We take care in where we store it, and are careful of what we allow around or on its cart. | 1 | 3 | 3 | LOW | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
11 | PH Sensor | Presentation/Demo | Acid Bath | Device fails to detect PH, or mis-reads | It could cause potential health/safety risk due to chemical burns. | Care must be taken when around the fish tank, and it should not be expected to be "clean" water. Exposure to it should be minimized, and be limited to Project FishWorks members. | 1 | 3 | 3 | LOW | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
12 | Financial | Project Completion | Money/ funding issues | Funds become unavailable | No longer able to purchase supplies and components for the project | Clear and constant communiction on external life factors by all members, and clear and transparent buying practices. | 3 | 4 | 12 | HIGH | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
13 | Communications | Project Completion | Team chemistry issues | Personal issues between team members arise | It could cause a break down in project coordination and potentially risk completion of milestones. | Clear and constant communiction on external life factors by all members, and a 'hide nothing ever' mentality to any level of issue about anything. | 3 | 5 | 15 | HIGH | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
14 | Technical/ Quality | Project Completion | PCB Design/ Nonworking boards | Node V2 or Base V1 do not function correctly | Would cause damage to components and require a redesign on the affected board. | Pray to the tech gods, and hope we did good in Altium. We have left enough time for revisions and another run should it be needed. | 2 | 4 | 8 | MEDIUM | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
15 | Schedule | Project Completion | Scheduling Conflict | Unknown events cause scheduling conflicts | Redistibution of load to the other members, or causing milestones or project aspects to be missed/ or left uncomplete | We have left enough room in the schedule that we should be able to handle at least a few unforseen curveballs. Otherwise it’s the good 'ol hike up them socks and start burning the candle at both ends. | 4 | 2 | 8 | MEDIUM | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
16 | Schedule | Project Completion | Ordering/ Deliveries Delayed | Unknown issues in deliveries and product ordering | Unnessisary expenses after rebuying parts, or finding alternate vendors that are able to deliver. | Leave enough room to account for worst case ordering practices and deliveries. | 3 | 3 | 9 | MEDIUM | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
17 | Resource | Project Completion | Camosun College Flooded | Camosun Campus becomes unavailable due to weather | As camosun is currently our main workshop/ place of work - we would be without somewhere to complete the project. | Have secondary workshop space, currently Kaylebs house in his garage. | 3 | 5 | 15 | HIGH | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
18 | Legal | Project Completion | Line Voltage Legal Issues | Legal complications in using our "Smart powerbar" causes us to not beable to use it. | As Line Voltage levels are strictly controlled in Canada, attempting to work with 120v AC could lead to being shut down by Canadian Regulators. | Use an Off-The-Shelf solution. | 2 | 2 | 4 | LOW | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
19 | Health Safety | Project Completion | Water becomes dangerously contaminated | Water becomes infected/ contaminated with dangerouse orginaisms | Team becomes sick due to exposure to the contaminated water. | Monitor the water, and cycle/change when needed. Consider using bleach to ensure it stays dead. | 1 | 3 | 3 | LOW | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
20 | Technical | Project Completion | Blazor/ other programing languages become unavailable. | Main programing language becomes unsupported and unavailable to use for our project. | Current progress and work into Web App is lost and we must find a new UI language. | We feel that this is nearly a non issue. Regardless, Blazor runs in .net, so we would be able to salvage a large portion of our work should it happen. | 1 | 2 | 2 | LOW | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED

## 2. Process Help
RISK MANAGEMENT PROCESS: OVERVIEW
1. The SCOPE, CONTEXT, and CRITERIA identifies the subject of the risk assessment. For Guidance, See Tab 3.
2. IDENTIFY risks by asking, "What could occur that would have an impact on our objectives?" Risks have three key elements: Event, causes, impacts.
3. Risks ANALYSIS involves ranking the likelihood and consequence using a 1-5 scale. For Guidance, See Tab 4.
4. In order to EVALUATE risks the group reviews the effectiveness and appropriateness of currents controls and determines what action to take, if any. For Guidance, See Tab 5.
5. Risk TREATMENT is the activity (s) you are going to implement to better manage your exposures. Your mitigations will reduce the likelihood and/or consequence of the risk event occurring.
NOTE: This template was taken from the BC Governments Risk Management for Government and Provincial Public Sector (Risk Management for Government & Provincial Public Sector - Province of British Columbia).

## 3. L&C Matrix
RISK RATING MATRIX (LIKELIHOOD AND CONSEQUENCE)
Likelihood and Consequence Descriptors for Risk Assessments
Likelihood | Rating | Criteria | Probability
Almost certain | 5 | It is expected to happen. Will certainly happen this fiscal year or during the three year period of the Service Plan. | 80% to 100% or once a year or more frequently
Likely | 4 | We expect it to happen. It would be surprising if this did not happen. | 61% to 79% or once every 3 yrs
Possible | 3 | Just as likely to happen as not. We don't expect it to happen, but there is a chance. | 40% to 60% or once every 5 yrs
Unlikely | 2 | Not anticipated. We won't worry about it happening. | 11% to 39% or once every 15 years
Almost certain not to happen | 1 | It would be surprising if this happened. There would have to be a combination of unlikely events for it to happen. | 0 to 10% or once every 25 yrs
Consequence | Rating | Criteria / Examples
Catastrophic | 5 | - Major problem from which there is no recovery. - Significant damage to organization credibility or integrity. - Complete loss of ability to deliver a critical program.
Major | 4 | - Event that requires a major realignment of how service is delivered. - Significant event which has a long recovery period. - Failure to deliver a major political commitment.
Moderate | 3 | - Recovery from the event requires cooperation across departments. - May generate media attention.
Minor | 2 | - Can be dealt with at a department level but requires Executive notification. - Delay in funding or change in funding criteria. - Stakeholder or client would take note.
Insignificant | 1 | - Can be dealt with internally at the business unit level. - No escalation of the issue required. - No media attention. - No or manageable stakeholder or client interest.
Risk Rating Matrix

## 4. Evaluation
RISK EVALUATION
In order to EVALUATE risks, the ADEQUACY OF CURRENT TREATMENTS (Column L) and ACTION (Column M) are determined ADEQUACY OF CURRENT TREATMENTS: Use the drop-down in Column L to identify the risk tolerance of the organization considering the current treatments. Choices include: - Non-existent: there are no current treatments identified in Column G (are not doing anything) - Inadequate: the current treatments (Column G) do not meet the organization's risk tolerance and need attention (are not doing enough) - Adequate: the current treatments (Column G) meet the organization's risk tolerance and no further action is required (are doing enough) - Robust: the current treatments (Column G) exceed the organization's risk tolerance (are doing too much) ACTION: Use the drop-down in Column M to identify the action the organization will take to respond to the risk, if any Choices incude: - Accept: no further action is required - Monitor: Accept and keep an eye on future trends that may impact the currently accepted risk tolerance - Treat: implement ADDITIONAL TREATMENTS to either reduce the likelihood (Column H) or reduce the impact if the risk event occurs (Column I) - Transfer: allocate the risk responsibility to another party through legal contract (e.g. hire another party and transfer the risk to them) - Avoid: do not pursue the objective to avoid the potential consequences identified that are outside of the risk tolerance of the organization TREND: Use the drop-down in Column N to identify the trend of the risk rating since the last reporting period (if applicable). Choices incude: - New Risk: the risk was not included in the last reporting period - Downward: the risk rating (Column J) has decreased since the last reporting period - Static: the risk rating (Column J) has not changed since the last reporting period - Upward: the risk rating (Column J) has increased since the last reporting period