## Table of Contents
TABLE OF CONTENTS
Main Budget
Base Station
Node Controller
TANK—Mechanical
DEVICE—Lighting
DEVICE—TempHum
DEVICE—AC Outlet
DEVICE—Leak
DEVICE—PH
Supplies
Potential Items
--data validation--

## Main Budget
Return to Table of Contents
| TOTAL PROJECT COST: |  |  |  |  | 144437.5935
| BILL OF MATERIALS (BOM) | [5 empty] | MILESTONES
| ITEM | % DONE | $ (EACH) | QUANTITY | TOTAL—$/ITEM |  | MILESTONE | DATE | WEEK | EST. $—BOM | EST. $—LBR/RENT | EST. $—TOTAL | TRUE $—BOM | TRUE $—LBR/RENT | TRUE $—TOTAL | DELTA
| Base Station | 20% | 75.127 | 5 | 375.635 |  | Tank—SET UP | 2024-09-16 | 3 | 907.2737 | 28434 | 29341.2737 | 907.2737 | 28434 | 29341.2737 | 0
| Node Controller | 20% | 23.184 | 15 | 347.76 |  | Budget Audit | 2024-09-27 | 5 | 907.2737 | 47390 | 48297.2737 | 1210.1585 | 47390 | 48600.1585 | 302.8848
| TANK—Mechanical | 80% | 729.1068 | 1 | 729.1068 |  | Node Controllers—BUILT | 2024-10-21 | 8 | 1255.0337 | 75824 | 77079.0337 |  |  | 0
| DEVICE—Lighting | 75% | 178.1669 | 1 | 178.1669 |  | Base Stations—BUILT | 2024-10-28 | 9 | 1630.6687 | 85302 | 86932.6687 |  |  | 0
| DEVICE—TempHum | 50% | 79.076 | 1 | 79.076 |  | Hardware Dev—COMPLETE | 2024-11-18 | 12 | 2187.3135 | 113736 | 115923.3135 |  |  | 0
| DEVICE—AC Outlet | 50% | 141.5288 | 1 | 141.5288 |  | App Programing—COMPLETE | 2024-11-18 | 12 | 2187.3135 | 113736 | 115923.3135 |  |  | 0
| DEVICE—Leak | 50% | 82.28 | 1 | 82.28 |  | Functional Demo | 2024-12-02 | 14 | 2267.5935 | 132692 | 134959.5935 |  |  | 0
| DEVICE—PH | 0% | 253.76 | 1 | 253.76 |  | Capstone Symposium | 2024-12-09 | 15 | 2267.5935 | 142170 | 144437.5935 |  |  | 0
| Supplies | 50% | 80.28 | 1 | 80.28 |  | Total | [7 empty] | 48600.1585 | 302.8848
| TOTAL—BOM: | 43.89% | 1642.5095 |  | 2267.5935
| LABOUR (LBR) EXPENSES | [5 empty] | LIVE AUDIT
| MEMBER | HOURLY | HRS/WK | WEEKLY | PROJECT TOTAL |  | MEASURE | VALUE
| Kayleb | 45 | 48 | 2160 | 32400 |  | Project Weeks | 15
| Eric | 45 | 48 | 2160 | 32400 |  | Earned Total | 63392.0549
| Sebastien | 45 | 48 | 2160 | 32400 |  | Planned Total | 48145.8645
| Braden | 45 | 48 | 2160 | 32400 |  | Actual Total | 48600.1585
| Excel Contractor (Jennifer) |  |  | 0 | 50 |  | Cost Performance Index (ev/ac) | 1.3044
| TOTAL—LBR: |  |  |  | 129650 |  | Schedule Performance Index (ev/pv) | 1.3167
[7 empty] | Cost Variance (ev-ac) | 14791.8965
RENT/UTILITIES (R/U)
| ITEM | $ (EACH) | PAYEES | COST/WK | TOTAL—R/U:
| Camosun Facilities Rental | 3130 | 4 | 834.6667 | 12520

## Base Station
Return to Table of Contents
PART NAME | MANUFACTURER | MANUFACTURER PN | SUPPLIER | SUPPLIER PN | #—TOTAL | #/UNIT | $/UNIT | $—SHIPPING | $—TOTAL | PAYEE | PURCHASED PRE-PROJECT | DATE REC'D | URL | NOTES/DESCRIPTION
CAP CER 10UF 10V Y5V 0805 | YAGEO | CC0805ZKY5V6BB106 | DigiKey | 311-1355-1-ND | 6 | Each | 0.184 |  | 1.104 |  | No
CAP0805 X5R 22UF 20% 35V | Cal-Chip Electronics, Inc. | GMC21X5R226M35NT | DigiKey | 4713-GMC21X5R226M35NTCT-ND | 2 | Each | 1.08 |  | 2.16 |  | No
CAP CER 0.1UF 50V X7R 0603 | Samsung Electro-Mechanics | CL10B104KB8NNNC | DigiKey | 1276-1000-1-ND | 4 | Each | 0.037 |  | 0.148 |  | No
CAP CER 560PF 50V X7R 0805 | YAGEO | CC0805KRX7R9BB561 | DigiKey | 311-1125-1-ND | 2 | Each | 0.19 |  | 0.38 |  | No
CAP CER 1UF 50V X7R 0805 | Samsung Electro-Mechanics | CL21B105KBFNNNG | DigiKey | 1276-6470-1-ND | 1 | Each | 0.16 |  | 0.16 |  | No
TVS DIODE 24VWM 70VC SOT23 | Diodes Incorporated | DESD1CAN2SOQ-7 | DigiKey | DESD1CAN2SOQ-7DICT-ND | 1 | Each | 0.56 |  | 0.56 |  | No
LED GREEN CLEAR 0805 SMD | Würth Elektronik | 150080VS75000 | DigiKey | 732-4986-1-ND | 1 | Each | 0.28 |  | 0.28 |  | No
CONN MOD JACK R/A 8P8C | Pulse Electronics | E5908-0T0343-L | DigiKey | 553-E5908-0T0343-L-ND | 1 | Each | 4.26 |  | 4.26 |  | No
CONN HEADER SMD 4POS 1MM | JST Sales America Inc. | BM04B-SRSS-TBT | DigiKey | 455-BM04B-SRSS-TBTCT-ND | 1 | Each | 1.44 |  | 1.44 |  | No
RES 4.7K OHM 1% 1/8W 0805 | YAGEO | RT0805FRE134K7L | DigiKey | 13-RT0805FRE134K7LCT-ND | 1 | Each | 0.15 |  | 0.15 |  | No
RES SMD 100 OHM 0.1% 1/8W 0805 | YAGEO | RT0805BRD07100RL | DigiKey | YAG1760CT-ND | 2 | Each | 0.25 |  | 0.5 |  | No
RES SMD 1.5K OHM 1% 1/8W 0805 | YAGEO | RT0805FRE071K5L | DigiKey | 13-RT0805FRE071K5LCT-ND | 1 | Each | 0.15 |  | 0.15 |  | No
RES SMD 100K OHM 1% 1/8W 0805 | YAGEO | RT0805FRE07100KL | DigiKey | YAG3359CT-ND | 1 | Each | 0.15 |  | 0.15 |  | No
RES 10K OHM 1% 1/8W 0805 | YAGEO | RC0805FR-1010KL | DigiKey | 13-RC0805FR-1010KLCT-ND | 2 | Each | 0.15 |  | 0.3 |  | No
SWITCH TACTILE SPST-NO 0.05A 12V | C&K | PTS 647 SN50 SMTR2 LFS | DigiKey | PTS647SN50SMTR2LFSCT-ND | 2 | Each | 0.28 |  | 0.56 |  | No
DC DC CONVERTER 5V | XP Power | TR10S05 | DigiKey | 1470-3971-ND | 1 | Each | 5.04 |  | 5.04 |  | No
IC TRANSCEIVER HALF 1/1 8SOIC | Microchip Technology | MCP2551T-I/SN | DigiKey | MCP2551T-I/SNCT-ND | 1 | Each | 2.09 |  | 2.09 |  | No
IC REG LINEAR 3.3V 600MA SOT25 | Diodes Incorporated | AP2112K-3.3TRG1 | DigiKey | AP2112K-3.3TRG1DICT-ND | 1 | Each | 0.54 |  | 0.54 |  | No
RF TXRX MOD BT WIFI PCB TH SMD | Espressif Systems | ESP32-C3-WROOM-02-N4 | DigiKey | 1965-ESP32-C3-WROOM-02-N4CT-ND | 1 | Each | 2.92 |  | 2.92 |  | No
MALE HEADER PINS |  |  | Shop Stock |  | 20 | Pin | 0.0146 |  | 0.292 | Kayleb | No

## Node Controller
Return to Table of Contents
PART NAME | MANUFACTURER | MANUFACTURER PN | SUPPLIER | SUPPLIER PN | #—TOTAL | #/UNIT | $/UNIT | $—SHIPPING | $—TOTAL | PAYEE | PURCHASED PRE-PROJECT | DATE REC'D | URL | NOTES/DESCRIPTION
CAP CER 10UF 10V Y5V 0805 | YAGEO | CC0805ZKY5V6BB106 |  |  | 7 | Each | 0.27 |  | 1.89
CAP CER 0.1UF 50V X7R 0603 | YAGEO | CC0603KRX7R9BB104 |  |  | 5 | Each | 0.14 |  | 0.7
CAP0805 X5R 22UF 20% 35V | Cal-Chip Electronics, Inc. | GMC21X5R226M35NT |  |  | 3 | Each | 1.07 |  | 3.21
CAP CER 560PF 50V X7R 1206 | YAGEO | CC1206KRX7R9BB561 |  |  | 2 | Each | 0.4 |  | 0.8
LED GREEN CLEAR 0805 SMD | Würth Elektronik | 150080VS75000 |  |  | 2 | Each | 0.27 |  | 0.54
TVS DIODE 24VWM 70VC SOT23 | Diodes Incorporated | DESD1CAN2SOQ-7 |  |  | 1 | Each | 0.57 |  | 0.57
RF TXRX MODULE WIFI PCB TRACE | Espressif Systems | ESP32-S3-WROOM-1-N8R2 |  |  | 1 | Each | 5.09 |  | 5.09
MICRO SD CARD CONNECTOR, 9 POSIT | Same Sky | MSD-4-A |  |  | 1 | Each | 0.5 |  | 0.5
CONN HEADER SMD 4POS 1MM | JST Sales America Inc. | BM04B-SRSS-TBT |  |  | 1 | Each | 1.42 |  | 1.42
CONN PWR JACK 2.5X5.5MM SOLDER | Würth Elektronik | 694108301002 |  |  | 1 | Each | 1.45 |  | 1.45
CONN MOD JACK R/A 8P8C | Pulse Electronics | E5908-0T0343-L |  |  | 1 | Each | 4.21 |  | 4.21
RES 10K OHM 1% 1/8W 0805 | YAGEO | RC0805FR-1010KL |  |  | 3 | Each | 0.15 |  | 0.45
RES SMD 0 OHM JUMPER 1/10W 0603 | Panasonic Electronic Components | ERJ-3GEY0R00V |  |  | 2 | Each | 0.15 |  | 0.3
RES ARRAY 8 RES 10K OHM 1206 | CTS Resistor Products | 746X101103JP |  |  | 1 | Each | 0.36 |  | 0.36
RES SMD 1.5K OHM 1% 1/8W 0805 | YAGEO | RT0805FRE071K5L |  |  | 2 | Each | 0.15 |  | 0.3
RES 4.7K OHM 1% 1/8W 0805 | YAGEO | RT0805FRE134K7L |  |  | 1 | Each | 0.15 |  | 0.15
RES 0.05 OHM 1% 2W 2512 | Stackpole Electronics Inc | CSRN2512FK50L0 |  |  | 1 | Each | 0.88 |  | 0.88
RES SMD 100 OHM 0.1% 1/8W 0805 | YAGEO | RT0805BRD07100RL |  |  | 2 | Each | 0.24 |  | 0.48
SWITCH TACTILE SPST-NO 0.05A 12V | C&K | PTS 647 SN50 SMTR2 LFS |  |  | 2 | Each | 0.27 |  | 0.54
DC DC CONVERTER 5V | XP Power | TR10S05 |  |  | 1 | Each | 4.98 |  | 4.98
IC REG LINEAR 3.3V 1A SOT223 | Diodes Incorporated | AZ1117IH-3.3TRG1 |  |  | 1 | Each | 0.58 |  | 0.58
IC TRANSCEIVER HALF 1/1 8SOIC | Microchip Technology | MCP2551T-I/SN |  |  | 1 | Each | 2.06 |  | 2.06
IC PWR SWITCH N-CHAN 1:1 TO252-5 | Infineon Technologies | ITS428L2ATMA1 |  |  | 1 | Each | 3.98 |  | 3.98
IC CURRENT MONITOR 1% SOT23-8 | Texas Instruments | INA219AIDCNR |  |  | 1 | Each | 2.7 |  | 2.7
BUZZER CMI -9650C-030 | Same Sky | CMI-9650C-030 | Digikey | 102-3740-ND | 1 | Each | 3.79 |  | 3.79 |  |  |  | https://www.digikey.ca/en/products/detail/same-sky/CMI-9650C-030/6012411 | Buzzer—Magnetic 3v 9.60mm Custom
SWITCH PUSH SPST-NO 3A 125V | E-Switch | PS1024ABLK | Digikey | EG2011-ND | 2 | Each | 2.56 |  | 5.12 |  |  |  | https://www.digikey.ca/short/jtbwwthp
1.3" TFT Colorful Display Module SPI |  |  | AliExpress |  | 1 | Each | 4.89 |  | 4.89 |  |  |  | https://www.aliexpress.com/item/1005007119301520.html?spm=a2g0o.productlist.main.27.77dbtPY6tPY61Q&algo_pvid=25dc966e-058f-42b1-9eec-fda56f3feeb8&algo_exp_id=25dc966e-058f-42b1-9eec-fda56f3feeb8-13&pdp_npi=4%40dis%21CAD%214.89%214.89%21%21%2124.80%2124.80%21%402101e62517274636100991041e3fae%2112000039464753243%21sea%21CA%213264091378%21X&curPageLogUid=CLZF6sh729Es&utparam-url=scene%3Asearch%7Cquery_from%3A
SanDisk Industrial 8GB Micro SD | SanDisk | SDSDQAF3-008G-I | Amazon |  | 1 | Each | 11.5 |  | 11.5 |  |  |  | https://a.co/d/76Hk7w9
WS2812B Neo-Pixel | BTF-LIGHTING |  |  |  | 10 | Each | 0.2687 |  | 2.687
Filement - Black PLA |  |  | Amazon |  | 300 | Grams | 0.03 |  | 9 | Kayleb | No | 4555000%

## TANK—Mechanical
Return to Table of Contents
PART NAME | MANUFACTURER | MANUFACTURER PN | SUPPLIER | SUPPLIER PN | #—TOTAL | #/UNIT | $/UNIT | $—SHIPPING | $—TOTAL | PAYEE | PURCHASED PRE-PROJECT | DATE REC'D | URL | NOTES/DESCRIPTION | Column1
1''X1''X8' ALUMINIUM SQUARE |  |  | Home Depot |  | 1 | Each | 67.18 |  | 67.18 | Braden | No | 4555000%
SCREWS |  |  | Home Depot |  | 1 | Each | 13.1 |  | 13.1 | Braden | No | 4555000%
0.5'' ALUMINIUM ANGLE BLACK |  |  | Home Depot |  | 2 | Each | 14.98 |  | 29.96 | Sebastien | No | 4555000%
MONO CLEAR SILICON |  |  | Home Depot |  | 1 | Each | 11.47 |  | 11.47 | Sebastien | No | 4555000%
24 AWG SILICONE ELECTRICAL WIRE CABLE 7 COLORS |  |  | Amazon |  | 1 | Each | 24.62 |  | 24.62 | Kayleb | No | 4555000% | https://a.co/d/08Xsi2SN
SUNSUN CIRCULATING PUMP |  |  | AliExpress |  | 1 | Each | 54.92 |  | 54.92 | Kayleb | No | 4555000%
FILEMENT - BLACK PLA |  |  | Amazon |  | 300 | Grams | 0.03 |  | 9 | Kayleb | No | 4555000%
2" ADPT SKF PVC FITTING |  |  | Andrew Sheret |  | 2 | Each | 2.39 |  | 4.78 | Kayleb | No | 4555000%
1 1/2" X 1" SPGXF PVC BUSHING |  |  | Andrew Sheret |  | 2 | Each | 2.9 |  | 5.8 | Kayleb | No | 4555000%
TUBE 3/4" ID X 1" OD VINYL |  |  | Andrew Sheret |  | 6 | Each | 2.19 |  | 13.14 | Kayleb | No | 4555000%
3/4" X 1/2" PVC 90 SKF |  |  | Andrew Sheret |  | 1 | Each | 0.91 |  | 0.91 | Kayleb | No | 4555000%
1/2" PVC 90 FXF |  |  | Andrew Sheret |  | 1 | Each | 1.42 |  | 1.42 | Kayleb | No | 4555000%
1" X 3/4" PVC BUSH MXF |  |  | Andrew Sheret |  | 1 | Each | 2.32 |  | 2.32 | Kayleb | No | 4555000%
1/2" X CLOSE SCH80 PVC NIPPLE |  |  | Andrew Sheret |  | 1 | Each | 0.68 |  | 0.68 | Kayleb | No | 4555000%
1" X CLOSE SCH80 PVC NIPPLE |  |  | Andrew Sheret |  | 1 | Each | 1.3 |  | 1.3 | Kayleb | No | 4555000%
3/4" PXF PVC ADPT |  |  | Andrew Sheret |  | 3 | Each | 2.54 |  | 7.62 | Kayleb | No | 4555000%
1-1/2" FLOW SENSOR |  |  | AliExpress |  | 1 | Each | 26.99 |  | 26.99 | Kayleb | No | 4555000%
3/4" FLOW SENSOR |  |  | AliExpress |  | 1 | Each | 6.48 | 2.91 | 9.39 | Kayleb | No | 4555000%
CLEAR PLASTIC JARS |  |  | Amazon |  | 3 | Each | 1.61 |  | 4.83 | Kayleb | No | 4555000%
1" BULKHEAD FITTING |  |  | Amazon |  | 2 | Each | 6.435 |  | 12.87 | Kayleb | No | 4555000%
YOGA MAT |  |  | Canadain Tire |  | 1 | Each | 13.43 |  | 13.43 | Sebastien | No | 4555000%
TANK - DISPLAY |  |  | Shop Stock |  | 1 | Each | 150 |  | 150 | Kayleb | Yes | 4555000% |  |  | 24
TANK - SUMP |  |  | Shop Stock |  | 1 | Each | 150 |  | 150 | Kayleb | Yes | 4555000% |  |  | 25
AW20 PUMP |  |  | ReefSuppy |  | 1 | Each | 56.99 |  | 56.99 | Kayleb | Yes | 4555000% |  |  | 26
PLEXI GLASS - CLEAR |  |  | Industrial Plastics |  | 2 | ft^2 | 19.29 |  | 38.58 | Kayleb | Yes | 4555000% |  |  | 27
PLEXI GLASS - TINTED |  |  | Industrial Plastics |  | 1.32 | ft^2 | 13.49 |  | 17.8068 | Kayleb | Yes | 4555000% |  |  | 28

## DEVICE—Lighting
Return to Table of Contents
PART NAME | MANUFACTURER | MANUFACTURER PN | SUPPLIER | SUPPLIER PN | #—TOTAL | #/UNIT | $/UNIT | $—SHIPPING | $—TOTAL | PAYEE | PURCHASED PRE-PROJECT | DATE REC'D | URL | NOTES/DESCRIPTION
LED POWER SUPPLIES 25.2W 36V 0.7A DIMMING LED PS IP67 | MEAN WELL | LPF-25D-36 | Mouser | 709-LPF25D-36 | 1 | Each | 67.18 |  | 67.18 | Sebastien | No | 5/22/2024 | https://www.mouser.ca/ProductDetail/709-LPF25D-36
LED POWER SUPPLIES 40.32W 36V 1.12A DIMMING FUNCTION | MEAN WELL | LPF-40D-36 | Mouser | 709-LPF40D-36 | 1 | Each | 42.31 |  | 42.31 | Sebastien | No | 5/22/2024 | https://www.mouser.ca/ProductDetail/709-LPF40D-36
BOX PC GRAY 5.51"L X 5.51"W | Hammond Manufacturing | 1554QGY | DigiKey | 164-1554QGY-ND | 1 | Each | 30.12 |  | 30.12 | Sebastien | No | 6/18/2024 | https://www.digikey.ca/en/products/detail/hammond-manufacturing/1554QGY/10481634?s=N4IgTCBcDaIIwDYAsBaOBWdSCKBxAmigHIAiIAugL5A
20X20X1MM THERMAL PADS |  |  | Amazon |  | 1 | Each | 11.19 |  | 11.19 | Kayleb | No | 4555000%
LED WHITE |  |  | AliExpress |  | 8 | Each | 0.23 |  | 1.84 | Kayleb | No | 4555000%
LED BLUE |  |  | AliExpress |  | 8 | Each | 0.22 |  | 1.76 | Kayleb | No | 4555000%
2N2222 |  |  | Shop Stock |  | 2 | Each | 0.52 |  | 1.04 | Kayleb | No | 4555000%
10V ZENER DIODE |  |  | Shop Stock |  | 1 | Each | 0.5312 |  | 0.5312 | Kayleb | No | 4555000%
100K ¼ RESISTOR |  |  | Shop Stock |  | 1 | Each | 0.028427 |  | 0.028427 | Kayleb | No | 4555000%
10K ¼ RESISTOR |  |  | Shop Stock |  | 1 | Each | 0.028427 |  | 0.028427 | Kayleb | No | 4555000%
2-CHANNEL RELAY MODULE FOR ARDUINO & RASPBERRY PI—5V |  |  | PiShop |  | 1 | Each | 4.95 |  | 4.95 | Sebastien | No | 4555000% | https://www.pishop.ca/product/2-channel-relay-module-for-arduino-raspberry-pi-5v/
POWER CORD |  |  | Shop Stock |  | 1 | Each | 11.1888 |  | 11.1888 | Kayleb | No | 4555000%
FILAMENT—BLACK PLA |  |  | Amazon |  | 200 | Grams | 0.03 |  | 6 | Kayleb | No | 4555000% |  | Enclosure Estimate

## DEVICE—TempHum
Return to Table of Contents
PART NAME | MANUFACTURER | MANUFACTURER PN | SUPPLIER | SUPPLIER PN | #—TOTAL | #/UNIT | $/UNIT | $—SHIPPING | $—TOTAL | PAYEE | PURCHASED PRE-PROJECT | DATE REC'D | URL | NOTES/DESCRIPTION
FILAMENT—BLACK PLA |  |  | Amazon |  | 200 | Grams | 0.03 |  | 67.18 | Kayleb | No | 4555000% |  | Enclosure estimate
SHT30D TEMP HUMIDITY |  |  | AliExpress |  | 1 | Each | 1.78 | 3.72 | 5.5 | Kayleb | No | 4555000%
DS18B20 TEMP PROBE |  |  | AliExpress |  | 2 | Each | 2.71 |  | 5.42 | Kayleb | No | 4555000%
4 PIN JST(PAIR) |  |  | Shop Stock |  | 1 | Each | 0.392 |  | 0.392 | Kayleb | No
3 PIN JST(PAIR) |  |  | Shop Stock |  | 2 | Each | 0.292 |  | 0.584 | Kayleb | No

## DEVICE—AC Outlet
Return to Table of Contents
PART NAME | MANUFACTURER | MANUFACTURER PN | SUPPLIER | SUPPLIER PN | #—TOTAL | #/UNIT | $/UNIT | $—SHIPPING | $—TOTAL | PAYEE | PURCHASED PRE-PROJECT | DATE REC'D | URL | NOTES/DESCRIPTION
HIGH POWER 2-CHANNEL RELAY |  |  | Amazon |  | 1 | Each | 27.14 |  | 27.14 | Eric | No | 4533200% | https://www.amazon.ca/dp/B077W1NVLM?ref=ppx_yo2ov_dt_b_fed_asin_title
4 GANG PLASTIC DEVICE BOX | South Wire | MSB4G | Amazon |  | 1 | Each | 18.52 |  | 18.52 | Eric | No | 4533300% | https://www.amazon.ca/dp/B00H8NUVO2?ref=ppx_yo2ov_dt_b_fed_asin_title
TAMPER RESISTANT RECEPTACLES | Leviton | T53325-W | SS |  | 2 | Each | 4.5 |  | 9 | Eric | No | 4200500%
GFCI PLUG ASSEMBLY |  |  | Amazon |  | 1 | Each | 24.57 |  | 24.57 | Eric | No | 4555300% | https://www.amazon.ca/dp/B06XPFB6ND?ref=ppx_yo2ov_dt_b_fed_asin_title
SCT013-015 15A /1V |  |  | Amazon |  | 1 | Each | 16.79 |  | 16.79 | Eric | No | 4555500% | https://www.amazon.ca/dp/B07X3393QT?ref=ppx_yo2ov_dt_b_fed_asin_title | Non-invasive Split Core
ADS1115 |  |  | Amazon |  | 0.33333 | Each | 21.84 |  | 7.28 | Eric | No | 4555100% | https://www.amazon.ca/dp/B0CTG4W5SN?ref=ppx_yo2ov_dt_b_fed_asin_title | 16-Bit i2C High Precision ADC Converter Development Board
4 GANG COVER PLATE | Leviton |  | SS |  | 1 | Each | 12 |  | 12 | Eric | No
1 GANG FILLER PLATE | Leviton |  | Amazon |  | 2 | Each | 7 |  | 14 | Eric | No | 4556200% | https://www.amazon.ca/gp/product/B000FA3A3Y/ref=ppx_yo_dt_b_asin_title_o00_s00?ie=UTF8&th=1
4 PIN JST(PAIR) |  |  | Shop Stock |  | 1 | Each | 0.392 |  | 0.392 | Kayleb | No
3 PIN JST(PAIR) |  |  | Shop Stock |  | 2 | Each | 0.292 |  | 0.584 | Kayleb | No
2N2222 |  |  | Shop Stock |  | 2 | Each | 0.52 |  | 1.04 | Kayleb | No | 4555000%
100K ¼ RESISTOR |  |  | Shop Stock |  | 1 | Each | 0.028427 |  | 11.1888 | Kayleb | No | 4555000%

## DEVICE—Leak
Return to Table of Contents
PART NAME | MANUFACTURER | MANUFACTURER PN | SUPPLIER | SUPPLIER PN | #—TOTAL | #/UNIT | $/UNIT | $—SHIPPING | $—TOTAL | PAYEE | PURCHASED PRE-PROJECT | DATE REC'D | URL | NOTES/DESCRIPTION
FILAMENT—BLACK PLA |  |  | Amazon |  | 200 | Grams | 0.03 |  | 67.18 | Kayleb | No | 4555000% |  | Enclosure estimate
WATER LEVEL SENSOR |  |  | AliExpress |  | 1 | Each | 0.22 | 3.12 | 13.1 | Kayleb | No | 4555000%
FLOAT SWITCH |  |  | Amazon |  | 1 | Each | 2 |  | 2 | Kayleb | No
3 PIN JST(PAIR) |  |  | Shop Stock |  | 1 | Each | 0.392 |  |  | Kayleb | No
2 PIN JST(PAIR) |  |  | Shop Stock |  | 1 | Each | 0.292 |  |  | Kayleb | No

## DEVICE—PH
Return to Table of Contents
PART NAME | MANUFACTURER | MANUFACTURER PN | SUPPLIER | SUPPLIER PN | #—TOTAL | #/UNIT | $/UNIT | $—SHIPPING | $—TOTAL | PAYEE | PURCHASED PRE-PROJECT | DATE REC'D | URL | NOTES/DESCRIPTION
ATLAS SCIENTIFIC PH SENSOR KIT | Atlas Scientific | KIT-101P | Robot Shop | RB-Atl-02 | 1 | Each | 247.76 |  | 247.76 | Camosun | No |  | https://ca.robotshop.com/products/atlas-scientific-ph-sensor-kit
FILAMENT—BLACK PLA |  |  | Amazon |  | 200 | Grams | 0.03 |  | 6 | Kayleb | No | 4555000% |  | Enclosure Estimate

## Supplies
Return to Table of Contents
PART NAME | MANUFACTURER | MANUFACTURER PN | SUPPLIER | SUPPLIER PN | #—TOTAL | #/UNIT | $/UNIT | $—SHIPPING | $—TOTAL | PAYEE | PURCHASED PRE-PROJECT | DATE REC'D | URL | NOTES/DESCRIPTION
6PCS SMALL BREADBORDS |  |  | Amazon |  | 1 | Each | 17.91 |  | 67.18 | Kayleb | No | 4555000%
24 AWG SILICONE ELECTRICAL WIRE CABLE 7 COLORS |  |  | Amazon |  | 1 | Each | 24.62 |  | 13.1 | Kayleb | No | 4555000% | https://a.co/d/08Xsi2SN

## --data validation--
Sebastien | Yes | cm^2
Eric | No | Each
Kayleb |  | ft^2
Braden |  | Grams
Camosun |  | Pin